## Prep.
Preparation - CHL Group Stage 2019/20
Item | Check Box | Area | Topic | To Do | Day | Meeting | Responsibility |  |  |  | Comments
[7 empty] | Infront/CHL | Club H | Club V | HB
1 |  | CHL/Infront and Club Commercial Partner Activities | Activities | Review planned CHL/Infront commercial partner activities with CR (if applicable) | P | - | VM | CR | - | - | P. 67/68 CM According to separate information from Enrico Brunold
2 |  | CHL/Infront and Club Commercial Partner Activities | Activities | Check with the CR whether the club plans any activities such as: - Commercial displays, sampling, promotions - Intermission - Award Ceremony | P | - | VM | CR | - | - | P. 67/68 CM Inform Enrico Brunold accordingly; commercial displays, sampling and intermission activities require approval
3 |  | CHL/Infront and Club Commercial Advertising | Overall Set-up | Check timetable for CHL/Infront commercial advertising implementation (ie. rink boards) at arena with CR | P | - | VM | CR | - | - | Set-up shall be done on GD-1 in the afternoon (at least for the 1st game) - If planned to install over night, please inform Enrico Brunold immediately
4 |  | Services and Facilities | Work Station | Ensure with the CR that a work station (table, chair with access to internet and printer (if possible) is provided for the VM | P | - | VM | CR | - | -
5 |  | Game Day Planning | Meetings | Confirm with CR that a meeting room for the following meetings is available: - Club meeting (GD-1 afternoon) - Broadcasting meeting (GD FO -04:00hrs) - Organisational meeting (GD FO -90:00min) - Debriefing meeting (shortly after game if feasible) | P | - | VM | CR | - | - | According to Run of show doc
6 |  | Game Day Planning | Meetings | Confirm the meeting time with CR for the following: - Advertising Check (GD-1 afternoon/upon arrival) - Club meeting (GD-1 afternoon/upon arrival) - Uniform check (GD-1 or GD) - LED, video, graphics and audio rehearsal (GD-1 or GD) | P | - | VM | CR | - | - | According to Run of show doc and separate checklist for video screen/jumbotron and LED boards and advertising check --> please inform Enrico Brunold if advertising implementation (ie. rink boards) is planned only on game day in the morning or over night)
7 |  | Ticketing | Tool/System Process | Check with CR whether the login to the ticketing tool works and whether the ticketing process is understood | P | - | VM | CR | - | - | As per separate communication from Enrico Brunold/Giannina Rageth Any issues shall be communicated to Enrico Brunold/Giannina Rageth right away
8 |  | Broadcasting | Operations | Get in contact with the BVM and confirm the following: - on-site arrival time - E2E time -> exactly FO-2hrs - broadcasting meeting (FO-4hrs) - received MRO document - staff list (positions rather than names) - on-site or remote production - standard production plan or extra cameras | P | - | VM | - | - | BVM | Staff list: forward to Uzi Kakuda (uzi.kakuda@infrontsports.com) except for AUT, FRA, GER, NOR & UK home games
9 |  | Broadcasting | Operations | Print out the following documents for the BVM: - 5 x MRO - 2 x End-to-end test running order (1x for VM) - 1 x TV Graphics checklist (1x for VM) - 1 x TISSOT clock insert guidelines (1 x for VM) | P | - | VM | - | - | - | Handout to BVM during broadcasting meeting Remind BVM that Tissot insertion timings are detailed on the MRO
10 |  | Game Day Planning | General | Review game footage on either CHL media platform (recurring clubs) or Youtube (new clubs) | P | - | VM | - | - | - | https://media.championshockeyleague.com Email: enrico.brunold@infrontsports.com Password: Season_201920
11 |  | Game Day Planning | General | Print out all documents needed on-site (from Infront ftp server) | P | - | VM | - | - | - | See: Overview VM Documents for Infront ftp server upload
12 |  | Game Day Planning | General | Download all respective files to an own USB stick (from Infront ftp server marked as "on stick as backup") | P | - | VM | - | - | - | See: Overview VM Documents for Infront ftp server upload
13 |  | Sport Regulations | Top Scorer | Check the current Top Scorer of the home and visiting club on chl.com and make sure the correct player number is attached on the front on the velcro patch above the club logo (number sets have been supplied) | P | - | VM | - | - | - | P. 112/113 CM (7.6 Top Scorer) 1st game of the season: captain unless otherwise communicated Next games: player with the highest points (if tied, more goals scored; if still tied: last one to score (goal or assist); should he not be able to play (injury, illness, any other important reasons), the runner up will be the Top Scorer Check (after first game): http://www.championshockeyleague.com/en/top-scorers
14 |  | Uniform and Equipment | Sponsors (CHL/Infront) | Check the club commercial advertising of the following elements of your home and visiting clubs: - Jersey - Helmet - Goalie equipment | P | - | VM | - | - | - | See: Club Commercial Partner Overview and get in touch with Enrico Brunold in case this information is missing. Check document "CHL blocked categories" in order to know about the exclusive industry sectors/branches

## Club
Club Meeting - CHL Group Stage 2019/20
Participants: VM, CR
Item | Check Box | Area | Topic | To Do | Day | Meeting | Responsibility |  |  |  | Comments
[7 empty] | Infront/CHL | Club H | Club V | HB
1 |  | Broadcasting | Operations | Ensure with CR that TVCO is briefed about the power break rules and that he/she'll take part at the broadcasting meeting | GD -1 | Club Mtg. | VM | CR | - | - | P. 52/53 CM Please also see the document "Power Break Procedure" on Infront ftp server
2 |  | Broadcasting | Operations | Ensure with CR that club media staff is in place after the game to get the coaches and players for the flash interviews | GD -1 | Club Mtg. | VM | CR | - | - | P. 49 CM
3 |  | CHL/Infront and Club Commercial Partner Activities | Commercial Displays & Sampling | Check with CR whether they plan any commercial display and/or sampling activities (in case they haven’t communicated it to CHL/Infront beforehand) | GD -1 | Club Mtg. | VM | CR | - | - | P. 67/68 CM If not communicated in advance, please immediately review with Enrico Brunold
4 |  | CHL/Infront and Club Commercial Partner Activities | Commercial Displays & Sampling | Review any CHL/Infront commercial partner planned commercial display and/or sampling activities with the CR | GD -1 | Club Mtg. | VM | CR | - | - | P. 67/68 CM As per separate information from Enrico Brunold (if applicable)
5 |  | CHL/Infront and Club Commercial Partner Activities | Intermission | Review any CHL/Infront commercial partner intermission activities planned with the CR | GD -1 | Club Mtg. | VM | CR | - | - | P. 45 / P. 67 CM As per separate information from Enrico Brunold (if applicable)
6 |  | CHL/Infront and Club Commercial Partner Activities | Intermission | Check with CR whether they plan any intermission activities (in case they haven’t communicated it to CHL/Infront beforehand); ensure with CR that any activities don't interfere with the ice cleaning time | GD -1 | Club Mtg. | VM | CR | - | - | P. 45 CM If not communicated in advance, please immediately review with Enrico Brunold
7 |  | Game Day Planning | Meetings | Set time with CR for final GD arena and set-up check | GD -1 | Club Mtg. | VM | CR | - | -
8 |  | Game Day Planning | Pucks | Ensure with CR that official CHL game pucks are used during game | GD -1 | Club Mtg. | VM | CR | - | - | P. 20 CM The pucks feature the CHL logo on one side & the respective club logo on the other side For warm-up: Regular club pucks may be used!
9 |  | Game Promotion and Fan Experience | Ice Cleaning Kids | Ensure with CR that ice cleaners' uniform is free of any club commercial advertising (if applicable) | GD -1 | Club Mtg. | VM | CR | - | - | P. 44 CM The kids shall not approach any players nor officials during their duty
10 |  | Game Promotion and Fan Experience | Cheerleaders | Ensure with CR that cheerleaders' uniform is free of any club commercial advertising (if applicable) | GD -1 | Club Mtg. | VM | CR | - | - | P. 43 CM
11 |  | Game Promotion and Fan Experience | Players Entrance/Tunnel | Ensure with the CR that any used player tunnel or the like is free of any club commercial advertising | GD -1 | Club Mtg. | VM | CR | - | - | P. 45 CM Clubs shall use their standard introduction and entrance of players
12 |  | Game Promotion and Fan Experience | Players Entrance/Tunnel | Check the timing of any intro show with the CR and adapt the run of show timing accordingly | GD -1 | Club Mtg. | VM | CR | - | - | P. 45 CM Important: as of FO -04.45min the timing is fix (players to be standing on blue lines, NO helmets) --> Exception: Games with participation of Belfast Giants The timing before can be adapted to the regular club intro show length
13 |  | Game Promotion and Fan Experience | Award Ceremony | Review any CHL/Infront commercial partner award ceremony planned with CR | GD -1 | Club Mtg. | VM | CR | - | - | P. 46 CM As per separate information from Enrico Brunold (if applicable)
14 |  | Game Promotion and Fan Experience | Award Ceremony | Check with CR whether they plan any award ceremony (in case they haven’t communicated it to CHL/Infront beforehand) | GD -1 | Club Mtg. | VM | CR | - | - | P. 46 CM - If not communicated in advance, please immediately review with Enrico Brunold; - Ensure that the club doesn’t bring its own club sponsors in connection with the CHL (NOT a CHL partner) - Ensure that the ceremony is not interfering with the flash interviews - timing is crucial!
15 |  | Game Promotion and Fan Experience | Mascot | Ensure with CR that - the mascot jersey is free of any club sponsor advertising - the mascot is not interfering with the TV production | GD -1 | Club Mtg. | VM | CR | - | - | P. 43 CM - Preferably mascot wears CHL jersey (if not possible, please make sure the jersey is free of any club commercial advertising) - Can be on the ice during the intro show and during the intermissions; in the stands during the game
16 |  | Game Promotion and Fan Experience | General | - Check the promotional material which the club produced and take pictures - The clubs have to use the CHL artwork for all promotional material - Any promotional material has to be free of any club commercial advertising and the CHL/Infront "commercial partner/sponsor bar" has to be included | GD -1 | Club Mtg. | VM | CR | - | - | P. 42 CM Send pictures to Enrico Brunold
17 |  | Game Statistics | Set-up | Check with CR that stats staff is briefed and will be on-site; hard- and software is in place; seats are reserved according to CM | GD -1 | Club Mtg. | VM | CR | - | - | P. 71/72 CM
18 |  | Press/Media and Photography | Press Conference | Ensure with CR that press conference room is set-up (with CHL backdrop) or standing position in front of CHL backdrop if no separate room is available | GD -1 | Club Mtg. | VM | CR | - | - | P. 34 CM - Press conference after the game is mandatory (EoG +15min); to be conducted by CMO in English (preferrably) or national language (translation for away coach must be in place); needs to be recorded (handling according to separate briefing by CHL (monika.reinhard@championshockeyleague.com)
19 |  | Press/Media and Photography | Interviews | Ensure with CR that players are informed about the "no helmet" for interviews policy | GD -1 | Club Mtg. | VM | CR | - | - | P. 33 CM
20 |  | Press/Media and Photography | Interviews | Ensure with CR that the head coach is informed about the flash interview and press conference obligation | GD -1 | Club Mtg. | VM | CR | - | - | P. 33/34 CM
21 |  | Services and Facilities | Accreditations | Check with CR that arena security is informed about CHL All Access, Broadcaster and Guest accreditations | GD -1 | Club Mtg. | VM | CR | - | - | P. 23 CM Holders of All Access (VM and CHL staff only) and Broadcaster accreditations need to be able to access the most direct walkways
22 |  | Services and Facilities | Work Station | Ensure with the CR that a work station (table, chair with access to internet and printer) is provided for the VM | GD -1 | Club Mtg. | VM | CR | - | - | Desk, chair, access to WIFI/LAN, printer
23 |  | Services and Facilities | Safety & Security, Power Lighting & Utilities, Ice Cleaning | Ensure with CR that all facility requirements are in place and any safety, security and access measures are respected and implemented according to the Club Manual | GD -1 | Club Mtg. | VM | CR | - | - | P. 24/25 CM
24 |  | Ticketing | Complimentary Tickets | Check/count the tickets per CHL/Infront commercial partner booking and ensure that the categories are correct | GD -1 | Club Mtg. | VM | CR | - | - | P. 26 CM As per ticketing tool overview (see email from Giannina Rageth) Any issues will have to be addressed with Giannina Rageth/Enrico Brunold right away!
25 |  | Ticketing | Complimentary Tickets | Ensure with CR that VIP guests will be served F&B (excl. alcoholic beverages) free of charge | GD -1 | Club Mtg. | VM | CR | - | - | P. 26 CM Any issues will have to be addressed with Enrico Brunold right away!
26 |  | Ticketing | Complimentary Tickets | Take a picture of the ticket | GD -1 | Club Mtg. | VM | CR | - | - | 1st game only Send it to Enrico Brunold
27 |  | Ticketing | Complimentary Tickets | Review with CR who will be inserting the not picked up tickets in the ticketing tool after the game | GD -1 | Club Mtg. | VM | CR | - | - | According to separate tickting guidelines provided by Giannina Rageth; Check ticketing guidelines & procedure (all tickets (also the once picked up) need to be confirmed) --> inform Giannina Rageth (giannina.rageth@infrontsports.com) in case of any issues

## Advert.Arena
Advertising and Arena Check - CHL Group Stage 2019/20
Participants: VM, CR
Item | Check Box | Area | Topic | To Do | Day | Meeting | Responsibility |  |  |  | Comments
[7 empty] | Infront/CHL | Club H | Club V | HB
1 |  | Broadcasting | Commentary Seats | Check on all confirmed commentary positions with the CR | GD -1 | Adv./Arena Check | VM | CR | - | - | P. 48 CM Main camera side; power, light, ISDN, ADSL/Wireless required
2 |  | Broadcasting | Flash Interviews | Check on flash interview position with CR | GD -1 | Adv./Arena Check | VM | CR | - | - | P. 49 CM Right off the ice where both clubs have easy access to; will be confirmed by BVM on GD
3 |  | CHL/Infront and Club Commercial Advertising | Player, Penalty and Scorekeeper Benches | Check club commercial advertising against club commercial partner overview or the blocked product categories overview | GD -1 | Adv./Arena Check | VM | CR | - | - | P. 59 CM Any exclusivity issues will have to be addressed with Enrico Brunold right away!
4 |  | CHL/Infront and Club Commercial Advertising | Rink Board | Check implementation according to Advertising Production & Implementation Guidelines | GD -1 | Adv./Arena Check | VM | CR | - | - | P. 58 CM TV/non-TV side, correct positions, correct length and heights, no club sponsor logo allowed
5 |  | CHL/Infront and Club Commercial Advertising | Rink Board | Check that sticker foil has been applied on top of the plexi glass | GD -1 | Adv./Arena Check | VM | CR | - | - | Does it fully cover the advertising below? Does it stick properly? Has it been applied properly?
6 |  | CHL/Infront and Club Commercial Advertising | Rink Board | Take a picture of all four sides of the rink as early as possible prior to the game plus one in all three directions from the main camera stand (left, straight, right) | GD -1 | Adv./Arena Check | VM | CR | - | - | Send pictures to Enrico Brunold; all games
7 |  | CHL/Infront and Club Commercial Advertising | Kick Board | Check that the club has covered (with yellow tape) or removed any existing club advertising (if applicable --> Germany only) | GD -1 | Adv./Arena Check | VM | CR | - | - | P. 58 CM Does it fully cover the advertising below? Does it stick properly? Has it been applied properly?
8 |  | CHL/Infront and Club Commercial Advertising | Platinum Circle | Check that the club has covered or removed any existing advertising (if applicable) | GD -1 | Adv./Arena Check | VM | CR | - | - | P. 59 CM Does it fully cover the advertising below? Does it stick properly? Has it been applied properly?
9 |  | CHL/Infront and Club Commercial Advertising | Plexiglass | Check that the club has removed any existing club advertising (if applicable) | GD -1 | Adv./Arena Check | VM | CR | - | - | P. 59 CM Any CHL/Infront commercial partner advertising will also have to be removed
10 |  | CHL/Infront and Club Commercial Advertising | Backdrop | Check implementation according to Advertising Production & Implementation Guidelines | GD -1 | Adv./Arena Check | VM | CR | - | - | P. 60 CM No club and club commercial partner advertising allowed
11 |  | CHL/Infront and Club Commercial Advertising | Safety net behind goals | Check whether there is any advertising on the safety net behind the goal; if so take picture | GD -1 | Adv./Arena Check | VM | CR | - | - | P. 54 CM In general in TV relevant area but will not have to be removed if club commercial advertising is printed on the net
12 |  | Exclusivity Concept | TV relevant area | Check exclusive zone/tv relevant area; ensure that no club commercial advertising is visible | GD -1 | Adv./Arena Check | VM | CR | - | - | P. 54 CM Final check: review the TV relevant area from the main camera at the OB van; game action view! Any exclusivity issues will have to be addressed with Enrico Brunold right away!
13 |  | Exclusivity Concept | TV relevant area | Check whether there is any advertising on the video screen/jumbotron; if yes --> check whether in tv view | GD -1 | Adv./Arena Check | VM | CR | - | - | P. 25 CM Final check: review the TV relevant area from the main camera at the OB van; game action view! Any exclusivity issues will have to be addressed with Enrico Brunold right away!
14 |  | Game Day Planning | Goal | Check that the goals (frame and net) are free of any club commercial advertising, goal supplier logos and any other branding | GD -1 | Adv./Arena Check | VM | CR | - | - | P. 20 CM Any other branding also includes club logos/branding
15 |  | Game Day Planning | Walkways | Get to know the arena: walk ways, locker rooms, hospitality area, OB van area, press and statistics area/seats, press conference room, offices, meeting rooms, etc. | GD -1 | Adv./Arena Check | VM | CR | - | -
16 |  | Merchandising | Articles | Check CHL merchandising products at club shop/booth and take pictures | GD -1 | Adv./Arena Check | VM | CR | - | - | P. 69/70 CM Send pics to Enrico Brunold; 1st game per round --> Clubs are allowed to sell their own merchandise (except the product range on p. 69 in the CM) and also national league merchandise Any exclusivity issues will have to be addressed with Enrico Brunold right away!
17 |  | Press/Media and Photography | Press/Media Seats | Check on the 20 press/media seats with CR | GD -1 | Adv./Arena Check | VM | CR | - | - | P. 30 CM Exact number of seats according to bookings by club
18 |  | Press/Media and Photography | Press/Media Seats | Check on the - 2 seats with desk for CHL website reporters - 6 seats with desk for CHL stats team | GD -1 | Adv./Arena Check | VM | CR | - | - | P. 30 CM
19 |  | Press/Media and Photography | Mixed Zone | Check on mixed zone area with CR | GD -1 | Adv./Arena Check | VM | CR | - | - | P. 32 CM Area where CHL backdrop can be placed and where both clubs have easy access to
20 |  | Press/Media and Photography | Press Conference | Check on press conference room with CR | GD -1 | Adv./Arena Check | VM | CR | - | - | P. 34 CM MANDATORY as of this season (15min after the game --> See RoS document) Clubs can also conduct the press conference in the mixed zone (standing position) if there is no separate room available ; CHL backdrops needs to be in place
21 |  | Press/Media and Photography | Photography Positions | Check on the 10 photographer positions with CR | GD -1 | Adv./Arena Check | VM | CR | - | - | P. 35 CM Exact number of positions according to bookings by club
22 |  | Ticketing | Hospitality | Check VIP hospitality area (not CHL exclusive) and walkways (if applicable) | GD -1 | Adv./Arena Check | VM | CR | - | - | P. 26 CM
23 |  | Ticketing | Complimentary Tickets | - Check on parking area (if applicable) - Ensure that the location is nearest to the arena entrance | GD -1 | Adv./Arena Check | VM | CR | - | - | P. 26 CM
24 |  | Ticketing | Complimentary Tickets | - Check on seats and walkways from entrance and/or hospitality area (if applicable) - Ensure that the seats are cat. 1/best seats | GD -1 | Adv./Arena Check | VM | CR | - | - | P. 26 CM
25 |  | Ticketing | Complimentary Tickets | - Check with CR that the tickets are deposited at the counter as per "Ticket Pick-up list" and as booked in via the Infront ticketing system - Check walkways | GD -1 | Club Mtg. | VM | CR | - | - | P. 26 CM Any issues shall be communicated to Enrico Brunold/Giannina Rageth right away

## VideoScreenAnnouncementLED
Video Screen/Jumbotron, LED Signage and Arena Announcement (Rehearsal) - CHL Group Stage 2019/20
Participants: VM, CR, MMO, (Arena Announcer) --> Can also take place on Game Day!
Item | Check Box | Area | Topic | To Do | Day | Meeting | Responsibility |  |  |  | Comments
[7 empty] | Infront/CHL | Club H | Club V | HB
1 |  | Services and Facilities | Public Address System, Scoreboard, Video Screen/ Jumbotron, LED Signage | Ensure with CR that the public address system, scoreboard, video screen/jumbotron (if applicable) and the LED signage (if applicable) are in place – at the same standard as for a domestic league game | GD -1 | Club Mtg. | VM | CR | - | - | P. 25 CM
2 |  | CHL/Infront and Club Commercial Partner Activities | Video screen/ jumbotron | Check CHL/Infront commercial video loop integration (incl. audio) and ensure that it will be played according to the timing on the run of show document | GD -1 | Club Mtg. | VM | CR, MMO | - | - | P. 67/68 CM
3 |  | CHL/Infront and Club Commercial Partner Activities | Video screen/ jumbotron | Check club commercial partner advertising integration (incl. audio) and ensure it will at all times be played after the CHL/Infront commercial video loop (if applicable) | GD -1 | Club Mtg. | VM | CR, MMO | - | - | P. 67/68 CM - Max. 6 club commercial partners and the same as for PA announcements - Video clip per club sponsor max. 30sec each - Video clips of club sponsors only to be shown after CHL sponsor video loop and only per run of show timing
4 |  | Game Promotion and Fan Experience | Video screen/ jumbotron | Check player cards (team rosters) of both teams | GD -1 | Club Mtg. | VM | CR, MMO | - | - | To be played out as per timing in Run of Show doc; To be obtained from CHL ftp server (according to separate information from CHL (Andreas Kötter; andreas.koetter@championshockeyleague.com)
5 |  | Game Promotion and Fan Experience | Video screen/ jumbotron | Check LGT TopScorer graphic (to be shown after team rosters) | GD -1 | Club Mtg. | VM | CR, MMO | - | - | To be played out after the team rosters (see Run of Show doc); supplied by Infront (Enrico Brunold)
6 |  | Game Promotion and Fan Experience | Video screen/ jumbotron | Check club promotion video of away team | GD -1 | Club Mtg. | VM | CR, MMO | - | - | To be played out as per timing in Run of Show doc; To be obtained from CHL ftp server (according to separate information from CHL (Andreas Kötter; andreas.koetter@championshockeyleague.com)
7 |  | Game Promotion and Fan Experience | Video screen/ jumbotron | Check CHL graphical elements integration and ensure that the MMO adheres to the jumbotron guidelines | GD -1 | Club Mtg. | VM | CR, MMO | - | - | P. 44 CM Jumbotron guidelines to be obtained from CHL ftp server (according to separate information from CHL (Andreas Kötter; andreas.koetter@championshockeyleague.com)
8 |  | Game Promotion and Fan Experience | Video screen/ jumbotron | Check if CHL Pico fan engagement URL is working (as per separate briefing from the CHL) | GD -1 | Club Mtg. | VM | CR, MMO | - | - | Separate briefing from the CHL direclty with the club (CHL responsible: Jannine Kamm (jannine.kamm@championshockeyleague.com)) --> separate URL for every club
9 |  | Game Promotion and Fan Experience | LED Signage | Check CHL LED branding integration and ensure that the CHL branding is shown on any LED boards within the TV relevant area | GD -1 | Club Mtg. | VM | CR, MMO | - | - | P. 44 & 67 CM The club can show own commercial advertising on the LEDs outside the TV relevant area pre-game, in intermissions and after the game, but not during the game (CHL artwork to be used at all times during the game)
10 |  | Services and Facilities | Public Address System | Ensure with CR that the - PA speaker is able to announce security messages in the language of visiting club or in ENG - PA speaker follows the run of show document (commercial messages only as per indication on the run of show document) | GD -1 | Club Mtg. | VM | CR | - | - | P. 25 CM
11 |  | CHL/Infront and Club Commercial Partner Activities | Announcements | Review/check club commercial partner advertising integration in PA announcements (if applicable) | GD -1 | Club Mtg. | VM | CR, MMO | - | - | P. 67/68 CM - To be played out as per timing in Run of Show doc; - Max. 6 club commercial partners and the same as for jumbotron (max. 6 club partners overall; ie 3 club partners with video spots, another 3 with PA announcements)

## Uniform
Uniform Check - Clubs - CHL Group Stage 2019/20
Present: VM, CR on GD-1 if possible (otherwise also on GD in the morning)
Present: VM, CRV on GD (as soon as the team arrives/the material manager is ready; the team might already be on-site on GD-1)
Item | Check Box | Area | Topic | To Do | Day | Meeting | Responsibility |  |  |  | Comments
[7 empty] | Infront/CHL | Club H | Club V | HB
1 |  | Uniform and Equipment | Uniform | Check that the players and goalkeepers only wear the centrally supplied uniform (jersey, pant shells and socks) | GD-1/ GD | Uniform Check | VM | CR | CRV | - | P. 61 CM Exception 1: Warm-up period (clubs allowed to wear own warm-up jerseys, but wearing CHL player kit is preferred because HB tapes the warm-up); Exception 2: No pant shells for goalkeepers supplied so they need to take off all velcro sponsor patches (clean approach), also no socks supplied for goalies
2 |  | Uniform and Equipment | Jersey | Check club commercial partner advertising badge/print, position and size on jersey according to guidelines in CM and club commercial partner overview | GD-1/ GD | Uniform Check | VM | CR | CRV | - | P. 61 & 65 CM 1 (one) club commercial partner not in blocked categories on right sleeve; exactly 8x22cm Any exclusivity issues will have to be addressed with Enrico Brunold right away!
3 |  | Uniform and Equipment | Jersey away team | Check main color of away team jersey to ensure enough contrast between the two main colors | GD-1/ GD | Uniform Check | VM |  | CRV | - | Home team chooses their main color, away team to adapt in order to ensure enough contrast --> Separte documentation on Infront ftp server (player kit colour match-up / player kits per team); if away team arrives with "wrong" player kit (ie. wrong colour), home team needs to adapt and play in their away kit
4 |  | Uniform and Equipment | Gloves | Check that all skaters will wear the supplied Warrior gloves | GD-1/ GD | Uniform Check | VM | CR | CRV | - | P. 61 It is mandatory for all skaters to wear the supplied Warrior gloves (all gloves of the same color: Red, navy blue or black); Exception 1: Warrior clubs (RBM); Exception 2: Players with hand/wrist injuries who need to wear special gloves for medical reasons (please inform Enrico Brunold immediately in this case) --> Equipment branding needs to be covered in this case (with tape) Any issues will have to be addressed with Enrico Brunold right away!
5 |  | Uniform and Equipment | Number, Names | Check that the implemented names and numbers are according to the guidelines | GD-1/ GD | Uniform Check | VM | CR | CRV | - | P. 65 CM & separate document "CHL jesey guidelines 201920" on Infront ftp server
6 |  | Uniform and Equipment | Goalkeeper Equipment | Check club sponsor on stick, blocker, catcher and leg pads according to club commercial partner overview | GD-1/ GD | Uniform Check | VM | CR | CRV | - | P. 62/63 CM 1 (one) club commercial partner allowed per equipment item (stick, blocker, catcher, leg pads) not in blocked categories; same advertising for all goal keepers; specially designed helmet is allowed but with same sponsor as skaters and no supplier logo (except Warrior) Any exclusivity issues will have to be addressed with Enrico Brunold right away!
7 |  | Uniform and Equipment | Goalkeeper Pants | Check that goalkeeper pants are free of any club commercial advertising | GD-1/ GD | Uniform Check | VM | CR | CRV | - | P. 61 CM
8 |  | Uniform and Equipment | Helmet | Check club commercial partner advertising on helmet according to club commercial partner overview | GD-1/ GD | Uniform Check | VM | CR | CRV | - | P. 61 CM 1 (one) club commercial partner not in blocked categories for all players (incl. goalkeeper); multiple stickers possible, no restrictions on size of stickers Any exclusivity issues will have to be addressed with Enrico Brunold right away!
9 |  | Uniform and Equipment | Helmet | Check helmet supplier logo and ensure that it's covered (unless it's a Warrior helmet); visor as well if needed | GD-1/ GD | Uniform Check | VM | CR | CRV | - | P. 61 CM Visor: only if strong colors and well visible
10 |  | Uniform and Equipment | Top Scorer Jersey | Ensure with CR/CRV that the Top Scorer wears the Top Scorer jersey and that the respective player number is attached to the velcro patch on the chest (number sets were supplied) | GD-1/ GD | Uniform Check | VM | CR | CRV | - | P. 64 & 112/113 CM The same club commercial partner on the jersey as for the regular player jersey; 1st game of the season: TopScorer = team captain (unless otherwise communicated) Any exclusivity issues will have to be addressed with Enrico Brunold right away!
11 |  | Uniform and Equipment | Top Scorer Helmet | No Top Scorer helmet stickers are supplied, therefore same regulations as for all player helmets | GD-1/ GD | Uniform Check | VM | CR | CRV | - | P. 64 CM Same regulations as for all player helmets, no specially designed Top Scorer stickers --> see item 8 & 9 above
12 |  | Uniform and Equipment | Apparel | Ensure with CR/CRV that Warrior apparel is worn by the relevant staff | GD-1/ GD | Uniform Check | VM | CR | CRV | - | P. 61 CM All staff visible at/behind the player bench during the game (does not apply to the staff on the scorekeeper's bench unless in TV view); except coach if wearing shirt/jacket; no club commercial partner advertising allowed; club logo is allowed
13 |  | Uniform and Equipment | Apparel | Ensure with CR/CRV that back-up goalie wears the Warrior cap/beanie if he usually wears a cap/beanie | GD-1/ GD | Uniform Check | VM | CR | CRV | - | P. 61 CM --> Not wearing any head gear is allowed
Uniform Check - Game Officials
Present: VM, GS, Game Officials (check with GS at broadcaster meeting about best time to conduct Game Official check --> Approx. 60min before the game)
Item | Check Box | Area | Topic | To Do | Day | Meeting | Responsibility |  |  |  | Comments
[7 empty] | Infront/CHL | Club H | Club V | HB
1 |  | Officials Uniform | General | Ensure that the officials wear the respective AJ referee jersey and Warrior helmet | GD | Uniform Check | VM GS | - | - | - | Check PDF document "CHL Referee Kit Season 2019/20" on seafile! Wearing a Warrior helmet is mandatory (supplied to all referees) --> Report to Enrico Brunold if one or more Game Officials don't wear a Warrior helmet
2 |  | Officials Uniform | General | Ensure that the AJ helmet and pant stickers are applied correctly | GD | Uniform Check | VM GS | - | - | - | Supply AJ stickers to GS at Broadcaster meeting Pants: one sticker one each side on the hemline of the pants (to the outside) to be attached slightly below the knee (can be taken off after the game; to be supplied at every game) Helmet: one sticker on the front of the helmet (only to be supplied if current sticker looks worn-off or not in place) --> only in first game, needs to stay attached to the helmets (i.e. not to be taken off after the game)
3 |  | Officials Uniform | General | Ensure that any existing equipment branding on the pants is removed or covered with black tape | GD | Uniform Check | VM GS | - | - | - | Pants have to be of black color!

## Broadc.
Broadcaster Meeting - CHL Group Stage 2019/20
Participants: VM, CR, CMO, TVCO, BVM, BFM
Item | Check Box | Area | Topic | To Do | Day | Meeting | Responsibility |  |  |  | Comments
[7 empty] | Infront/CHL | Club H | Club V | HB
1 |  | Broadcasting | Services and Facilities | Review all broadcast related facilities and ensure everything is according to plan and approve set-up | GD | Broadc. Mtg. | VM | CR | - | BVM, BFM | P. 47 CM - Check if your venue has a reverse camera position (if player benches situated below main camera) --> See camera plan of your venue on Infront ftp server - Check stability and position (eg.: centered, view obstruction) of camera platforms - Check commentary positions (eg.: centered, view obstruction, internet, desk lamp, etc) -> please take note and submit feedback in debrief report
2 |  | Broadcasting | Services and Facilities | Check with broadcaster if help is required in any areas and review any issues | GD | Broadc. Mtg. | VM | - | - | BVM, BFM
3 |  | Services and Facilities | Accreditations | Inform BVM about accreditation zones | GD | Broadc. Mtg. | VM | CR | - | BVM, BFM | P. 23 CM
4 |  | Broadcasting | Operations | Confirm and take note of broadcast operations workflow and HB production team roster and roles | GD | Broadc. Mtg. | VM | - | - | BVM | - Quantity of staff on-site and roles of staff? - OB van on-site or remote? - Uplink on-site (SNG truck with clear view to the Southern horizon) or remote? -> please take note and submit feedback in debrief report
5 |  | Broadcasting | Operations | Hand out the following documents to the BVM & print-out one copy each for you): - 5 x MRO - 2 x End-to-end test running order - 1x Tissot clock insert guidelines - 1 x TV Graphics checklist | GD | Broadc. Mtg. | VM | - | - | BVM
6 |  | Broadcasting | Operations | Hand out 2 USB sticks to the BVM for the recording of the game (cam 1 clean feed) Check with the BVM when they can be picked-up after the game | GD | Broadc. Mtg. | VM | - | - | BVM, BFM | Distribute USB sticks to clubs (home & away) after the game
7 |  | Game Day Planning | Run of Show | Review run of show and ensure that all parties stick to countdown to face-off and also intermission times | GD | Broadc. Mtg. | VM | CR, CMO, TVCO | - | BVM, BFM | Double-check that the new set-up with FO -4.45 all players standing on blue lines (no helmets) followed by CHL anthem, national anthem of away team ending with national anthem of home team is clear and understood by all parties involved -- > Exception: Games with participation of Belfast Giants (only CHL anthem to be played)
8 |  | Game Day Planning | Run of Show | Ensure with CR that CRM provides the VM or BVM with the line-up form at FO-90min | GD | Broadc. Mtg. | VM | CR | - | BVM, BFM
9 |  | Game Day Planning | Run of Show | Confirm with CR that all clocks (arena, locker rooms, etc.) show the right and the same time | GD | Broadc. Mtg. | VM | CR | - | - | Check if they are synchronized with the clock in the OB van
10 |  | Broadcasting | Power Break | Review power break procedure with TVCO, BVM, BFM and ensure with TVCO that red lamp (or other set-up) at time keeper bench is available and working - if not an alternative solution between the TVCO and the BFM will have to be found | GD | Broadc. Mtg. | VM | TVCO | - | BVM, BFM | P. 52/53 CM
11 |  | Broadcasting | Flash Interviews | Check & confirm position of flash interview area | GD | Broadc. Mtg. | VM | CR, TVCO | - | BVM, BFM | P. 49 CM
12 |  | Broadcasting | Flash Interviews | Review flash interview request timing and procedure with BVM, BFM, club staff | GD | Broadc. Mtg. | VM | CR, TVCO | - | BVM, BFM | - At FO 3 plus 15min BFM to confirm desired 2 players for flash interviews to VM (coach of both clubs always for interviews) - VM and respective club staff to inform player benches accordingly (talk to CMO about the best possible approach to inform club staff on bench - Usually no information at all, players will simply be stopped at player tunne by CMO) - VM and respective club staff (usuall CMO) to ensure right after game that respective players are present for interviews
13 |  | Broadcasting | Flash Interviews | Confirm with BVM who will be conducting the flash interviews | GD | Broadc. Mtg. | VM | - | - | BVM, BFM | - Should it not be a commentator - it should be either a dedicated reporter or trained and experienced BFM - Double check the CHL branded microphone cover is used for all world feed interviews - Double-check that the language requirements are understood for the flash interviews and get back to Enrico Brunold if unsure: 1. Home team Head Coach in Club Native Language 2. Visiting team Head Coach in English 3. Home team Player in English 4. Visiting team Player in Club Native Language
14 |  | Broadcasting | Flash Interviews | Ensure with CMO that no live interviews (via mobile) are being conducted by the press | GD | Broadc. Mtg. | VM | CMO | - | -
15 |  | Broadcasting | Flash Interviews | Handout 2 CHL microphone covers to BVM and collect again after flash interviews | GD | Broadc. Mtg. | VM | - | - | BVM, BFM | It is very important that the microphone covers are collected again after the flash interviews!
16 |  | Broadcasting | Flash Interviews | Ensure with BVM that CHL microphone covers are used for the flash interviews | GD | Broadc. Mtg. | VM | - | - | BVM, BFM | Own covers are not allowed!
17 |  | Broadcasting | In-Arena Studios | Check on the studio positions (if applicable) | GD | Broadc. Mtg. | VM | CR, TVCO | - | BVM, BFM | P. 49 CM As per separate information from Chris Hurst or Enrico Brunold; Check if it has non obstructive view on the rink
18 |  | Broadcasting | Mixed Zone | Check position of mixed zone (if applicable for HB) | GD | Broadc. Mtg. | VM | CR, TVCO | - | BVM, BFM | P. 32 CM
19 |  | Broadcasting | Press Conferences | Check press conference room | GD | Broadc. Mtg. | VM | CR, TVCO | - | BVM, BFM | P. 34 CM Post-game press conference mandatory as of this season, but no HB obligation (handled by the CMO)
20 |  | Broadcasting | Game Enhancements | Ensure with CR that the head coach has been informed about the procedure | GD | Broadc. Mtg. | VM | - | - | BVM, BFM | P. 34 & 49 CM --> Obligation to take part in flash interview & post-game press conference --> Detailed information in CHL sport bulletin to clubs (from Alex Jäger)
21 |  | Broadcasting | Game Enhancements | Ensure with BVM that 2 clip mics and transmitters/receivers are being prepared for micing up the head coaches | GD | Broadc. Mtg. | VM | - | - | BVM, BFM | P. 51 CM --> detailed information in CHL sport bulletin to clubs (from Alex Jäger) Make sure that the club (new clubs especially) are fully aware and the head coach has been informed
22 |  | Broadcasting | Game Enhancements | Ensure with BVM that head coaches will be mic'd FO -10min at locker rooms | GD | Broadc. Mtg. | VM | - | - | BVM, BFM | Timing to be adapted if too early/too late for some coaches --> BVM to be informed accordingly
23 |  | Game Day Planning | Meetings | Confirm the following separate meetings with BVM: - Exclusive zone/tv relevant area and graphics check time with BVM (FO -03.00hrs) - End-to-end test (FO -02.00hrs) | GD | Broadc. Mtg. | VM | - | - | BVM | - Graphics check: the timing may be adapted but please make sure to have enough time should there be any issues regarding the exclusive zone/tv relevant area and/or the TV graphics (see TV graphics checklist on Infront ftp server) - End-to-end test: FO -02.00hrs timing is IMPERATIVE
24 |  | Game Day Planning | Meetings | Define time for debriefing meeting with all parties involved if feasible | GD | Broadc. Mtg. | VM | CR, CMO, TVCO | - | BVM, BFM | As most staff wants to leave the premises as soon as they are done with their tasks, please be in touch with all parties during the game, take notes and make sure to cover all aspects of the debriefing report --> in this case, no separate meeting is needed: Exception: CHL staff on site! In this case, the debriefing meeting has to take place
25 |  | Press/Media and Photography | Club Media Activities | Check with CR whether they will film the game for technical purposes; if so check camera position with BVM | GD | Broadc. Mtg. | VM | CR | - | BVM | P. 39 CM In the event that the main camera platform is also accommodating commentary position, the BVM will advise if there is room on the platform for technical filming. If not, Club should find position elsewhere.
26 |  | Press/Media and Photography | Club Media Activities | Check with CMO that camera storage is in place for any non-CHL/Infront broadcasters camera storage and that rules are in place | GD | Broadc. Mtg. | VM | CMO | - | - | P. 39 CM
Separate checklists for
Graphics check -> Graphics (GFX) checklist
End-to-end test -> End-to-end test running order

## Organ.
Organizational Meeting - CHL Group Stage 2019/20
Participants: VM, GS, CR, CRV, CMO, TVCO, CRM
Item | Check Box | Area | Topic | To Do | Day | Meeting | Responsibility |  |  |  | Comments
[7 empty] | Infront/CHL | Club H | Club V | HB
1 |  | Services and Facilities | Accreditations | Inform relevant parties about accreditation zones | GD | Organ. Mtg | VM, GS | CR | CRV | - | P. 23 CM
2 |  | Game Day Planning | Run of Show | Review run of show in detail and ensure that all parties adhere to the set timing for activities; it is imperative that the game starts on time | GD | Organ. Mtg | VM, GS | CR, CMO | CRV | - | P. 19 CM -> separate document "RoS" Players on the ice without helmet at FO -4:45 for CHL & both national anthems!
3 |  | Game Day Planning | Meetings | Inform all relevant parties about set debriefing time | GD | Organ. Mtg | VM, GS | CR, CMO, TVCO | - | -
4 |  | Broadcasting | Flash Interviews | Inform CRV about flash interview procedure (as discussed during broadcasting meeting) | GD | Organ. Mtg | VM | TVCO | CRV | - | - At FO 3 plus 15min BFM to confirm desired 2 players for flash interviews to VM (coach of both clubs always for interviews) - VM and respective club staff to inform player benches accordingly (talk to CMO about the best possible approach to inform club staff on bench - Usually no information at all, players will simply be stopped at player tunnel by CMO) - VM and respective club staff (usually CMO) to ensure right after game that respective players are present for interviews
5 |  | Press/Media and Photography | Press Conference | Infrom CRV about press conference procedure | GD | Organ. Mtg | VM | CMO | CRV | - | P. 34 CM Post-game press conference mandatory! Please make sure both clubs are aware of the procedure (starts at EoG +15min) and that the coaches will be present
6 |  | Broadcasting | Game Enhancement | Inform CRV about mic'ing of head coaches (as discussed during broadcasting meeting); FO -10min at locker rooms | GD | Organ. Mtg | VM | - | CRV | - | P. 49 CM --> detailed information in CHL sport bulletin to clubs (from Alex Jäger); Mic'ing done by TV production crew; Timing to be adapted if too early/too late for some coaches --> BVM to be informed accordingly
7 |  | Broadcasting | Operations | Inform CRV when they will receive the USB stick after the game (with cam 1 clean feed) | GD | Organ. Mtg | VM | - | CRV | -
8 |  | Sport Regulations | Top Scorer | Check the current Top Scorer of the home and visiting club on chl.com and make sure the correct player number is attached on the front on the velcro patch above the club logo (number sets have been supplied) | GD | Organ. Mtg | VM | CR, CRM | CRV | - | P. 112/13 CM (7.6 Top Scorer) 1st game: captain Next games: player with the highest points (if tied, more goals scored; if still tied: last one to score (goal or assist); should he not be able to play (injury, illness, any other important reasons), the runner up will be the Top Scorer Check (after first game): http://www.championshockeyleague.com/en/top-scorers
9 |  | Broadcasting | Power Break | Review power break procedure with GS and ensure with GS that he will review the procedure with the referees | GD | Organ. Mtg | VM, GS | - | - | - | P. 52/53 CM According to Power Breaks Policies and Procedures; or alternative procedure (regarding red light on time keeper bench) as agreed between TVCO, BVM, BFM
10 |  | Officials Uniform | General | Handout AJ pant badges and helmet stickers to the GS; GS to handout stickers to Game Officials and to ensure that they will be applied; check with GS about timing for Game Officials Uniform Check | GD | Organ. Mtg | VM, GS | - | - | - | Pants: one AJ sticker on each side on the pants on the hemline (to the outside), slightly below the knee so the stickers do not get wet and fall off --> All games Helmet: one AJ sticker in the front of the helmet --> First game only, or if one of the stickers is damaged or looks worn-off (helmet sticker not to be detached after the game)
11 |  | Broadcasting | Flash Interviews | Show the relevant parties the flash interview area | GD | Organ. Mtg | VM | CMO | CRV | -
12 |  | Press/Media and Photography | Mixed Zone | Show the relevant parties the mixed zone | GD | Organ. Mtg | VM | CMO | CRV | -
13 |  | Press/Media and Photography | Press Conference | Show the relevant parties the press conference room | GD | Organ. Mtg | VM | CMO | CRV | -

## Terminology
Terminology
BFM | Broadcaster Floor Manager
BVM | Broadcaster Venue Manager
CMO | Club Media Officier
CR | Club Representative
CRM | Club Result Manager
CRV | Club Representative Visiting
LTS | LGT Top Scorer
EoG | End of Game
FO | Face off
GD (-1 / +1) | Game Day
GS | Game Supervisor
GO | Game Officials
HB | Host Broadcaster
MMO | Multi Media Operator
P | Preparation
TVCO | TV Coordinator (Club)
VM | Venue Manager